## WBS & Schedule
WBS ID | Task / Phase Description | Assigned Owner | Start Date | End Date | Duration (Days) | Predecessors | Progress | Status
1.0 | Project Initiation & Team Formation | Sandesh Chaudhary | 2026-09-01 | 2026-09-05 | 5 | - | 100% | COMPLETED
2.0 | Requirements Gathering & SRS Baseline | Morgan Vance | 2026-09-08 | 2026-09-19 | 10 | 1.0 | 100% | COMPLETED
3.0 | System Architecture & UML Modeling | Alex Rivera | 2026-09-22 | 2026-10-03 | 10 | 2.0 | 100% | COMPLETED
4.1 | Module 1: User Auth & RBAC API | Jordan Lee | 2026-10-06 | 2026-10-17 | 10 | 3.0 | 100% | COMPLETED
4.2 | Module 2: Question Bank & Exam Config | Jordan Lee | 2026-10-20 | 2026-10-31 | 10 | 4.1 | 100% | COMPLETED
4.3 | Module 3: Real-time Assessment Engine | Taylor Swift | 2026-11-03 | 2026-11-14 | 10 | 4.2 | 100% | COMPLETED
4.4 | Module 4: Anti-Cheating & AI Proctoring | Taylor Swift | 2026-11-17 | 2026-11-28 | 10 | 4.3 | 100% | COMPLETED
5.0 | QA Test Execution & RTM Validation | Casey Kim | 2026-12-01 | 2026-12-12 | 10 | 4.4 | 100% | COMPLETED
6.0 | Final Deployment & Project Sign-off | Sandesh Chaudhary | 2026-12-15 | 2026-12-19 | 5 | 5.0 | 100% | COMPLETED

## Gantt Timeline
WBS ID | Task / Phase Description | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12
1.0 | Project Initiation & Team Formation | bar: W1
2.0 | Requirements Gathering & SRS Baseline | bar: W2 to W3
3.0 | System Architecture & UML Modeling | bar: W4 to W5
4.1 | Module 1: User Auth & RBAC API | bar: W6 to W7
4.2 | Module 2: Question Bank & Exam Config | bar: W8
4.3 | Module 3: Real-time Assessment Engine | bar: W9 to W10
4.4 | Module 4: Anti-Cheating & AI Proctoring | bar: W10 to W11
5.0 | QA Test Execution & RTM Validation | bar: W11 to W12
6.0 | Final Deployment & Project Sign-off | bar: W12